## 1,2,3 July
Area | Responsible Person | Issue | Deadline | Status
Web scraping | Shruti | How to webscrape around a particular infringement in general | 2-3 July | Ongoing
| Shruti/Sushant | Is it possible to webscraping as a whole (by defining conditions-hastags,words,phrases, time frame, stakeholders name and so on) than having to go through each infringement manually? | 2-3 July | Ongoing
| Shruti/Sushant | How to tackle the time of the reaction issue(For eg-Stakeholders can reach to a decision in a weeks or a months time) | 2-3 July | Ongoing
| Shruti/Sushant | Check overall feasibility of web scraping an APIS | 2-3 July | Ongoing
Overall Analysis | Sushant | Basic data set cleaning | 2-3 July | Done
| Sushant | Deciding on the stakeholder (breaking down the email also) with rationale behind it | 2-3 July | Done
| Sushant | Basic research on how to tackle the language barrier issue | 2-3 July | Ongoing
| Sushant | Make a overall idea/chart of how to proceed with the project-what information for which stakeholders are to be collected from which channels using which technical tool. | 2-3 July | Ongoing
Questions | Shruti/Sushant | All the difficulties and limitations note it down for further dicsussion(possibly in excel/word) | 2-3 July | Ongoing
Email | Shruti/Sushant | Email progress,limiations, choices/assumptions made till now and ask compelling questions(backed by research). | 4th July | Ongoing

## Checklist
Step | Details | Status | Comments
Identify Decision | Select a specific decision for analysis (e.g., 12-14 Apr 2024 for Zarco #5)
Scraping Data | - Tool: Apify<br>- Platform: Instagram, blogs<br>- Focus: Public comments, posts from riders, teams, influencers, and official MotoGP pages
Data Collection - Public | Collect comments on Instagram posts related to the decision
Data Collection - Riders | Identify posts from the involved rider and their team (e.g., Zarco #5, Team LCR)
Data Collection - Journalists | Gather articles or blog posts discussing the decision
Data Collection - Influencers | Scrape comments from popular MotoGP influencer pages
Data Collection - Internal | Note internal memos or statements if available
Data Processing | - Categorize Comments: Label comments by stakeholder type<br>- Sentiment Analysis: Classify as positive, negative, or neutral<br>- Aggregate Data: Summarize
Reporting | - Compile Findings: Create report with sentiment results<br>- Visualize Data: Use graphs and charts to present sentiment distribution

## Riders & Teams
Data collection-riders, riders teams and public.
Step | Details | Step | Details
Identify Decision | 12-14 Apr 2024 for Zarco #5 | Search for Rider's Posts
Riders |  | Go to Instagram | Open Instagram on web or mobile.
Wikipedia Search - Event | Search for "2024 MotoGP COTA" on Wikipedia | Search for Relevant Posts | Use keywords and hashtags (e.g., #COTA2024, #Zarco, #MotoGP).
Wikipedia Search - Riders | Find the list of riders for the event or try using MotoGP website | Check Timeline | Look at dates around the event (e.g., April 12-14, 2024).
Rider Profile - Wikipedia | Access each rider's Wikipedia profile | Identify Relevant Posts | Look for posts by Johann Zarco discussing the decision.
Rider Profile - Social Media | Identify official social media accounts of riders | Collect Post URL and Content | Save URL and note down content.
Collect Data - Posts/Comments | Collect recent posts and comments related to the decision | Search for Team's Posts
Teams |  | Go to Instagram | Open Instagram on web or mobile.
Wikipedia Search - Event | Search for "2024 MotoGP COTA" on Wikipedia | Search for Relevant Posts | Use keywords and hashtags (e.g., #COTA2024, #Zarco, #MotoGP).
Wikipedia Search - Teams | Find the list of participating teams for the event | Check Timeline | Look at dates around the event.
Team Profile - Wikipedia | Access each team's Wikipedia profile | Identify Relevant Posts | Look for posts by Team LCR discussing the decision.
Team Profile - Social Media | Identify official social media accounts of teams | Collect Post URL and Content | Save URL and note down content.
Collect Data - Posts/Comments | Collect recent posts and comments related to the decision | Search for Other Riders' Posts
|  | Go to Instagram | Open Instagram on web or mobile.
|  | Search for Relevant Posts | Use keywords and hashtags (e.g., #COTA2024, #MotoGP).
|  | Check Timeline | Look at dates around the event.
|  | Identify Relevant Posts | Look for posts by other riders discussing the decision.
|  | Collect Post URL and Content | Save URL and note down content.
Search for Other Teams' Posts
|  | Go to Instagram | Open Instagram on web or mobile.
|  | Search for Relevant Posts | Use keywords and hashtags (e.g., #COTA2024, #MotoGP).
|  | Check Timeline | Look at dates around the event.
|  | Identify Relevant Posts | Look for posts by other teams discussing the decision.
|  | Collect Post URL and Content | Save URL and note down content.
Gather Reactions and Comments
|  | Identify the Post | Use collected URLs to locate posts.
|  | Scroll Through Comments | Gather reactions and comments.
|  | Use Scraping Tools | Use scraping tools if comments are too many to manually check.
|  | Analyze Comments for Sentiment | Manually analyze or use tools for sentiment analysis.

## Considerations
Considerations regarding the scope of data collection(Search for Relevant Posts)
Step | Details
Expand Hashtags | Use additional relevant hashtags and keywords related to the event, rider, team, and infractions (e.g., #JohannZarco, #TeamLCR, #MotoGP2024, #MotoGPStewards, #RacingPenalty).
Manual Search | Perform manual searches using different variations and combinations of keywords and hashtags.
Related Hashtags | Look at the hashtags used in relevant posts and add those to your search list.
Advanced Tools | Utilize advanced social media monitoring tools or scraping tools to automate searches and identify relevant posts.
Engagement Metrics | Focus on posts with high engagement (likes, comments, shares) as they are more likely to be relevant.
Following the Network | Follow the network of users who frequently engage with MotoGP content, including fans, journalists, influencers, and other riders.
Acknowledging Limitations | Recognize that some data might still be missed due to the vast and dynamic nature of social media.
Considerations regarding the scope of data collection regarding timeline(Search for Relevant Posts)
Step | Details | Comments
Check Timeline (Manual) | Manually look at dates below each post to ensure they fall within the event dates. | Verify dates visually on Instagram posts.
Check Timeline (Automated) | Use Apify's filtering options to automatically filter posts by event dates. | Automate the date verification process.
Approach | Step | Details | Timeline | Comments | Assumptions
Pilot Project | Immediate Reactions | Collect sentiments within 0-48 hours post-decision | 0-48 hours | Focus on Instagram posts and comments | Most immediate reactions are likely to be from direct stakeholders (riders, teams)
| Short-term Reactions | Collect sentiments up to 1 week post-decision | Up to 1 week | Include riders, teams, and public comments | Short-term sentiments capture a broader public response
| Key Stakeholders | Prioritize collecting data from riders and teams | Immediate and short-term |  | Directly affected stakeholders provide the most relevant insights
Full-Fledged Deliverable | Immediate Reactions | Collect sentiments within 0-48 hours post-decision | 0-48 hours | Focus on Instagram posts and comments | Immediate reactions capture the raw, unfiltered sentiment
| Short-term Reactions | Collect sentiments up to 1 week post-decision | Up to 1 week | Include riders, teams, and public comments | Allows time for more thoughtful responses
| Medium-term Reactions | Monitor ongoing discussions and posts | 1 month | Capture evolving sentiment | Sentiments evolve as more information and perspectives emerge
| Long-term Reactions | Periodically check for relevant mentions and discussions | 3-6 months | Track sustained discussions | Long-term sentiments reflect the lasting impact of the decision
Considerations regarding the scope of data collection regarding timeline(Search for Relevant Posts)
Step | Details | Status | Comments | Output
Install Libraries | Install pandas, langdetect, and googletrans | Done | Using pip | Libraries installed successfully
Load Excel File | Read comments from Excel file into DataFrame | Pending | Update file path as needed | DataFrame containing comments
Detect Language | Detect language of each comment | Pending | Use langdetect library | Column with detected languages
Translate Comments | Translate non-English comments to English using googletrans | Pending | Use googletrans library | Column with translated comments
Save to Excel | Save the translated comments back to Excel | Pending | Update output file path as needed | New Excel file with translated comments
Extra Considerations
Problem Encountered | Step | Details | Comments | Solution
Not enough or not a single post | Use General MotoGP Hashtags | Search for #MotoGP, #MotoGPRace, #MotoGP2024 |  | Expand search to include broader and related hashtags.
Not enough or not a single post | Search for Relevant Posts | Use hashtags like #COTA2024, #Zarco, #MotoGP |  | Check posts from MotoGP official accounts and other major stakeholders.
Not enough or not a single post | Use Time Filters | Focus on posts around the event date |  | Extend the timeframe of posts being searched and include a few days before and after the event.
Not enough or not a single post | Search for Relevant Articles | Look for articles related to the event and decision |  | Check multiple sources and widen the search criteria to related topics and broader keywords.
No Posts or Reactions Found | If no posts or reactions are found, consider sentiment neutral | This indicates no strong opinions | No one has posted or reacted | Document as neutral sentiment due to lack of engagement.
Bias in terms of popularity | Check Posts from Other Riders | Look for posts by other riders and teams | Manual check or scraping tools | Ensure to cover both popular and less popular riders by extending the search timeline.
Bias in terms of popularity | Identify Relevant Blogs and Pages | List popular MotoGP blogs and stakeholder pages |  | Include a mix of well-known and niche blogs to balance the coverage.
Bias in terms of popularity | Collect and Analyze Comments | Collect comments from these articles |  | Analyze comments from both mainstream and less popular articles to ensure diverse perspectives.
Verify the authenticity of the account by looking for the verified badge (blue tick) or checking the follower count and content.
Reason/Title | Rationale
Authenticity | Ensures the data is genuinely from the rider, providing reliable insights. Eliminates the risk of analyzing content from fake or imposter accounts.
Credibility | Verified accounts are trusted sources, enhancing the validity of the sentiment analysis. Ensures the sentiments analyzed are credible and authoritative.
Focus | Reduces noise by excluding irrelevant or misleading content from unverified accounts. Ensures analysis is concentrated on relevant, accurate data.
Consistency | Maintains a consistent data source, facilitating a more accurate comparison over time. Ensures that the sentiment analysis is based on uniform and reliable data.
Ethical Considerations | Avoids potential misinformation spread by unofficial accounts. Ensures ethical data collection by focusing on authentic sources.
Data Collection Methodology
Account Verification
To ensure the authenticity of the data collected from Instagram, we verified the accounts of MotoGP riders. This was done by:
1. Searching for the Account: Using Instagram's search bar to find the official account of each rider.
2. Checking for the Blue Checkmark: Verified accounts were identified by the presence of a blue checkmark next to the account name.
Rationale for Including Followers Numbers in the Dataset
Influence on Public Sentiment: Riders with a larger number of followers have a greater reach, making their opinions and posts more influential. This can shape public sentiment significantly. Conversely, riders with fewer followers might have a more niche but dedicated audience, whose sentiment might differ.
Engagement Metrics: Including follower numbers allows for analyzing engagement levels. Riders with more followers often receive more comments and interactions, which can be crucial for sentiment analysis. Comparing this with riders who have fewer followers helps to understand the variance in engagement and sentiment impact.
Comparative Analysis: By comparing riders' follower counts, we can identify patterns in public sentiment. For example, high-engagement posts from popular riders may indicate broader public opinion trends, while posts from less-followed riders might reveal more specific or intense sentiments from a smaller, possibly more passionate group.
Identifying Key Influencers: Knowing which riders have the most followers helps identify key influencers within the MotoGP community. This can be useful for understanding whose opinions carry the most weight. In contrast, identifying those with fewer followers can highlight grassroots or emerging influences.
Data Visualization: Follower counts enhance data visualization, allowing for a more nuanced analysis of how rider influence correlates with public sentiment and engagement. This can help in contrasting the reach and impact of riders with varying levels of popularity.
Including in Methodology
Yes, including this information in your methodology strengthens your data collection approach by ensuring a comprehensive analysis of public sentiment influenced by key figures in the MotoGP community, while also providing insights into the engagement and influence of less popular riders.
Methodology in Report
Include the following steps in your data collection methodology:
1. Account Verification: Use the verification badge to confirm official accounts.
2. Follower Count: Record the number of followers to gauge reach and influence.
3. Sentiment Weighting: Adjust the impact of sentiments based on follower count to reflect true public opinion accurately.
Your approach to cross-verifying comments exported from Instagram posts with a list of riders, their teams, and media outlets' accounts is a sound strategy, particularly for ensuring the accuracy and relevance of sentiment analysis. Here's why this method is effective and how you can optimize it:
Why This Approach is Effective:
1. Distinguishing Public Sentiment from Stakeholder Opinions: By identifying and excluding comments from riders, teams, and media outlets, you can focus on the general public's sentiment. This is crucial because comments from stakeholders might reflect personal or organizational biases, rather than the broader public opinion you aim to analyze.
2. Accuracy in Analysis: Ensuring that your sentiment analysis is based on comments from the general public (fans and followers) will provide a more accurate representation of public sentiment towards the decisions made by the MotoGP Stewards Panel. Stakeholders' comments could skew the results if not identified and handled separately.
3. Enhanced Data Integrity: Cross-verifying against your list helps in maintaining the integrity of your data set. It ensures that the analysis is based on the intended data sample, making your conclusions more robust and reliable.
Assumptions and Rationale for Including "No Response" as Neutral in Sentiment Analysis
Assumption:
In the context of the sentiment analysis for the provided MotoGP-related dataset, "No Response" from riders, teams, or stakeholders is treated as a neutral sentiment (score of 0). This assumption is based on the idea that the absence of a response neither conveys a positive nor negative sentiment explicitly.
Rationale:
1. Capturing Passive Reactions:
Contextual Significance: In the highly scrutinized environment of MotoGP, stakeholders like riders and teams are typically vocal about their views on penalties and race incidents. A lack of response may imply indifference, a deliberate choice to stay neutral, or a strategic decision to avoid further controversy. By treating these non-responses as neutral, we ensure that the analysis captures both active and passive reactions, providing a more comprehensive view of the sentiment landscape.
2. Avoiding Data Exclusion Bias:
Inclusion of All Data Points: Excluding "No Response" cases might lead to a skewed analysis, particularly when these cases form a significant portion of the dataset. By including them as neutral, we avoid potential biases that could arise from ignoring a large subset of the data. This approach ensures that our sentiment analysis reflects the reality that not all stakeholders choose to voice their opinions publicly.
3. Reflecting Real-World Behavior:
Common Practice in Sentiment Analysis: In sentiment analysis, it is common to treat the absence of a sentiment as neutral, especially in contexts where silence can be interpreted as a lack of strong feelings either way. This aligns with real-world behavior where individuals or organizations might choose not to comment on specific incidents, thereby not influencing the overall sentiment in either direction.
4. Maintaining Analytical Integrity:
Consistency in Sentiment Scoring: By assigning a neutral score to "No Response," we maintain consistency in our scoring system. This approach allows us to apply a uniform methodology across all data points, ensuring that the sentiment analysis is systematic and unbiased, leading to more reliable insights.
5. Enhanced Understanding of Stakeholder Dynamics:
Insight into Stakeholder Engagement: Including "No Response" as neutral provides additional insights into the level of engagement from different stakeholders. If a significant number of stakeholders consistently do not respond, it might indicate a broader trend of disengagement or strategic neutrality, which is valuable information for understanding the dynamics within the MotoGP community.
6. Balanced Sentiment Representation:
Preventing Sentiment Skew: Without treating "No Response" as neutral, the sentiment analysis could become overly positive or negative, depending on the active responses. Including neutral responses helps to balance the sentiment distribution, offering a more accurate representation of the overall mood within the dataset.
Conclusion:
Including "No Response" as neutral in the sentiment analysis provides a balanced, comprehensive, and contextually appropriate view of the dataset. This approach acknowledges the potential significance of silence in the MotoGP environment and ensures that the analysis remains inclusive, consistent, and reflective of real-world stakeholder behavior.
Understanding the Context:
Rider's Sentiment: The rider’s sentiment is already clear from their post, and you've categorized it accordingly.
Team's Sentiment: When the team quotes or references the rider's post without adding any additional commentary or their own sentiment, the team is essentially endorsing the rider's sentiment by default. This means that the team is aligning itself with the rider’s perspective.
How to Treat This:
1. Mirror the Sentiment: If the team simply quotes or re-shares the rider's content without any additional comments, the team's sentiment should be considered the same as the rider's.
For example, if the rider's sentiment was neutral or negative, you can apply the same sentiment to the team.
2. Consider the Lack of Additional Input: If the team had the opportunity to add its own commentary but chose not to, this might indicate a passive endorsement or a lack of a strong opinion, which could lean toward neutral.
In Your Example:
Rider's Post: Fabio Quartararo's post expresses regret and acknowledgment of mistakes, which is slightly negative but with a hopeful tone for improvement.
Team's Reaction (Quoting the Rider): The team's sentiment can be interpreted as mirroring the rider's, given that they did not add anything further. Therefore, if Fabio's post is considered neutral-to-negative, the team’s sentiment should be treated similarly.
Recommendation:
In your dataset:
Label the team's sentiment as Neutral-Negative when they merely quote the rider's sentiment without any additional input.
If there is additional commentary from the team that deviates from or amplifies the rider's sentiment, you should analyze it separately.
This approach ensures consistency and acknowledges the implicit endorsement of the rider's sentiments by the team.